## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | NG – 6/17/2020 – passed
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | NG – 6/17/2020 – passed
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | NG – 6/17/2020 – failed: Included Non-alphanumeric characters and didn't include space bar; Passed on 6/18/20
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | NG – 6/17/2020 – passed
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | NG – 6/17/2020 – passed
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | NG – 6/17/2020 – passed
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | NG – 6/17/2020 – passed
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | FA – 6/22/2020 – passed
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | FA – 6/22/2020 – passed
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | FA – 6/22/2020 – passed
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | FA – 6/22/2020 – passed
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | FA – 6/22/2020 – passed
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | FA – 6/22/2020 – passed
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | FA – 6/22/2020 – passed
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | FA – 6/22/2020 – passed
As a Player I want to sign-out of the WebCheckers app so that my username becomes available for someone else to use. | Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) |  |  | Pass | FA – 7/1/2020 – passed
| Given that I am signed-in when I do click on the sign-out link then I expect to be taken to the home page. |  |  | Pass | FA – 7/1/2020 – passed
| Given that I have signed-out when another player that is signed-in and on the home page, then that player cannot see my previous username. |  |  | Pass | FA – 7/1/2020 – passed
| Given that I have signed-out when I am on the Home page, then I expect the number of active users to be updated to be correct. |  |  | Pass | FA – 7/1/2020 – passed
As a Player I want to make a simple move so that I can participate in a game of Checkers.. | Given a single piece (or a king piece), when I move that piece to an adjacent square forward, away from the player, then I expect this to be a valid move. |  |  | Pass | NG - 7/5/2020 - Passed
| Given a single piece, when I move that piece to a white square, then I expect this to be an invalid move. |  |  | Pass | NG - 7/5/2020 - Passed
| Given a single piece (or a king piece), when I move that piece to a space that is already occupied, then I expect this to be an invalid move |  |  | Pass | NG - 7/5/2020 - Passed
| Given a single piece, when I move that piece to an adjacent square backward, toward the player, then I expect this to be an invalid move. |  |  | Pass | NG - 7/5/2020 - Passed
As a Player I want to create a King piece so that I can move diagonally both forward and backward. | Given a single piece when the piece moves onto the furthest row from my view then I expect the piece to turn into a king. |  |  | Pass | AF; 7/8 - passed
| Given a king piece, when I move that piece to an adjacent square backward, toward the player, then I expect this to be a valid move. |  |  | Pass | AF; 7/8 - passed
As a Player I want to forfeit a game so that the game can end early. | Given that I am in a Checkers game, when I resign from the game, then I expect to be removed from that game and returned to the Home page. |  |  |  |  | Pass | NG - 7/15/2020 - Passed
| Given that I'm in a WebCheckers game when my opponent resigns then I expect that I will be notified that my opponent has resigned, and given an option to return to the Home page. |  |  |  |  | Pass | NG - 7/15/2020 - Passed
| Given that I've resigned from a WebCheckers game, when I'm on the Home page, then I expect that I can join another WebCheckers game with the player I was previously in a game with. |  |  |  |  | Pass | NG - 7/15/2020 - Passed
As a Player I want to make a simple jump move so that I can capture my opponent's piece. | Given an opponent is in an adjacent dark square to one of my pieces, when I jump over the opponent piece diagonally, then I expect the opponent's piece to be removed from the board. |  |  |  |  | Pass | FA - 7/15/2020 - Passed
| Given any of the pieces, when I try to attempt to jump in a non-diagonally direction, then I expect this to be an invalid move. |  |  |  |  | Pass | FA - 7/15/2020 - Passed
| Given one of my own pieces is in an adjacent dark square, when I attempt to jump over my own piece diagonally, then I expect this to be an invalid move. |  |  |  |  | Pass | FA - 7/15/2020 - Passed
| Given one of my king pieces and an opponent is in an adjacent dark square that is backward from myself, when I try to jump in diagonally backward, then I expect the opponent's piece to be removed from the board. |  |  |  |  | Pass | FA - 7/15/2020 - Passed
| Given there is a jump move available on the board, when I try to make a simple move, then I expect this to be an invalid move. |  |  |  |  | Pass | FA - 7/15/2020 - Passed
As a Player I want to know that the game has ended so that I can choose to play another game. | Given that I am in game when I capture all pieces, then I expect the game page to update to the 'Game Over' state with a message saying I have captured all of the pieces. |  |  |  |  | Pass | AF; 7/18 - failed due to the fact that when a Player wins by capturing all pieces, the message says that the Player who lost has all of their pieces blocked. AF Tested again on 7/18 - passed
| Given that I am in a game when all my pieces are blocked, then I expect the game page to update to the 'Game Over' state with a message saying that all my pieces are blocked. |  |  |  |  | Pass | AF; 7/18 - passed
| Given that I am in a game that is over, when I click on the 'Exit' button, then I expect to be redirected to the Home page. |  |  |  |  | Pass | AF; 7/18 - passed
As a Player I want to make a multi-jump move so that I can capture multiple of my opponents pieces in one turn. | Given that I have made a valid move, I have the ability to 'backup' that move before I submit, and the piece I moved will return to its original position. |  |  |  |  | Pass | NG - 7/15 - Passed
| When I 'backup' a jump move, I expect the piece that would have been captured to still remain. |  |  |  |  | Pass | NG - 7/15 - failed due to that when backing up a multi jump move it only backs up the newest jump move made in the multi-jump move. NG test again on 7/18 - passed
| Given one of my own pieces, when I make a single jump over an opponent's piece and another single jump is available, then I expect to be able to make that second jump (including any consecutive jumps after the second). |  |  |  |  | Pass | NG - 7/15 - passed
| Given one of my own pieces, when I make a multi-jump move, then I expect every opponent's piece my piece jumped over to be removed from the board. |  |  |  |  | Pass | NG - 7/15 - passed
| Given a king piece, when I make a multi-jump move, then I expect to be able to jump forward and backward at any point in the multi-jump move. |  |  |  |  | Pass | NG - 7/15 - passed
| Given I make an invalid move, I expect to see a message telling me why the move is invalid. |  |  |  |  | Pass | NG - 7/15 - passed
| Given I have a multi-jump move available, and I try to submit my turn without completing the entire multi-jump move, I expect to see a message telling me why I can't submit my turn. |  |  |  |  | Pass | NG - 7/15 - passed
As a Player I want to watch another game so that I can pass the time. | Given when I am signed in when I click on a player who is currently in a game then I expect to watch the game as a spectator. |  |  |  |  | Pass | NG - 7/22 - passed
| Given when I am spectating a game when I click on the exit button then I expect to be redirected to the home page. |  |  |  |  | Pass | NG - 7/22 - passed
| Given when I am spectating a game when a player makes move then I expect to game board be updated. |  |  |  |  | Pass | NG - 7/22 - passed
| Given when I am spectating a game when the game ends then I expect to be shown a message explaining why the game ended. |  |  |  |  | Pass | NG - 7/22 - passed
As a Player I want to look up an old checkers game by it's ID so that I can watch the game at a later date. | Given that I am signed in and on the Home Page when click on a archived game then I expect to be redirected to the GameView in replay mode |  |  |  |  | Pass | NG - 7/24 - passed
| Given that I have just finished a game with another player, when I return to the Home page then I expect to see the game we just played show up under 'Stored Games'. |  |  |  |  | Pass | NG - 7/24 - passed